## Drawing list
Drawing number | Title | Discipline | Sheet size | Scale | Current revision | Status | Issue 01 | Issue 02 | Issue 03 | Issue 04 | Issue 05 | Issue 06 | Issue 07 | Issue 08 | Notes
AWF-ARC-2001 | Terminal Building Ground Floor Plan | Architectural | A1 | 1:100 | C | Issued for construction |  |  | B |  | C |  |  |  | Gate line moved 600mm east at C
AWF-STR-1100 | Wharf Deck Framing Plan | Structural | A1 | 1:200 | B | Issued for construction |  |  | A | B |  |  |  |  | Pile P14 relocated at B
AWF-STR-1101 | Wharf Deck Framing Sections | Structural | A1 | 1:50 | B | Issued for construction |  |  | A | B
AWF-STR-1102 | Pile Schedule | Structural | A3 | NTS | A | Issued for construction |  |  |  | A |  |  |  |  | First issued with the pile schedule update
AWF-CIV-3005 | Ferry Berth Civil Layout | Civil | A1 | 1:250 | A | Issued for review |  | A | [6 empty] | Awaiting marine approval
AWF-ELE-4200 | Terminal Power Distribution Layout | Electrical | A1 | 1:100 | B | Issued for construction | A |  |  |  |  | B |  |  | Revision A superseded by B
AWF-HYD-5010 | Terminal Hydraulic Services Plan | Hydraulic | A1 | 1:100 | 0 | As-constructed | [6 empty] | 0 |  | Verified against site markup

## Issues
Issue | Date issued | Transmittal reference | Purpose of issue | Issued to | Notes
Issue 01 | 2025-12-11 | TR-0009 | For construction | Aurora Wharf JV
Issue 02 | 2026-01-21 | TR-0021 | For review | Aurora Wharf JV
Issue 03 | 2026-02-10 | TR-0030 | For review | Aurora Wharf JV | Design review set
Issue 04 | 2026-03-01 | TR-0039 | For construction | Aurora Wharf JV | Pile schedule update
Issue 05 | 2026-03-15 | TR-0042 | For construction | Aurora Wharf JV
Issue 06 | 2026-03-24 | TR-0047 | For construction | Aurora Wharf JV
Issue 07 | 2026-04-03 | TR-0051 | For as-constructed record | Aurora Wharf FM | Handover pack
Issue 08

## How to use
Lunr drawing list
A ready-to-use drawing list and issue sheet: every drawing on one row, and the revision it went out at on every issue.
How to use it
1. List every drawing in the set on its own row, with its number, title, discipline, sheet size, and scale.
2. Before each issue, fill the next row on the Issues sheet with the date, the transmittal reference, the purpose of issue, and who it goes to.
3. In that issue's column on the drawing list, enter the revision of each drawing that went out. Leave the cell empty for a drawing that was not issued.
4. Update the current revision and status of each drawing you issued, so the first columns always show where the set stands.
5. Read down an issue column to see exactly what one transmittal carried. Read across a row to see a drawing's whole issue history.
6. When the eight issue columns fill, insert more to the left of Notes and add matching rows to the Issues sheet.
The columns
Drawing number. The controlled drawing number. Keep the format consistent across the project.
Title. The drawing title as printed in the title block.
Discipline. The discipline the drawing belongs to. Pick from the dropdown.
Sheet size. The paper size the drawing is set up for. Pick from the dropdown.
Scale. The drawing scale, for example 1:100, or NTS for not to scale.
Current revision. The latest revision issued, for example A, B, C, or 0.
Status. Where the drawing sits in its life. Pick from the dropdown.
Issue 01 to Issue 08. The revision issued at each issue. Look the issue up on the Issues sheet for its date, transmittal, and recipient.
Notes. Anything else worth recording against the drawing.
Dropdowns
Discipline: Architectural, Structural, Civil, Mechanical, Electrical, Hydraulic, Fire, Survey, Landscape, Geotechnical, General.
Sheet size: A0, A1, A2, A3, A4.
Status: Draft, Issued for review, Issued for construction, As-constructed, Superseded.
Purpose of issue, on the Issues sheet: For information, For review, For approval, For tender, For construction, For as-constructed record.
All accept your own value if your project uses a different term.
When a spreadsheet stops keeping up
A list like this works until a revision is typed into the wrong issue column, or the files that went out no longer match the cells that say they did. When that happens, move the record into drawing management software that issues transmittals against drawings held under revision control, records the revision of every file sent, and logs every change. See lunr.app.
Bring this drawing list into Lunr with your numbers preserved: www.lunr.app/document-control
Get the latest version of this template: www.lunr.app/templates/drawing-list